Sample Scope and Sequence of Professional Learning Engagement

This overview represents the services for one client of the professional learning partner.

| Curriculum or Content Area | i-Ready Classroom Mathematics (K–8 Mathematics) |  |  |
| --- | --- | --- | --- |
| Type of Professional Learning | Ongoing for Teachers and Leaders (Year 3 of implementation), plus Coaching by i-Ready (Instructional Coaching – Leader Pathway add-on) |  |  |
| Total Cost Range | - Less than $50,000 - $50,000 - $100,000 - $100,001 - $500,000 |  | - $500,001 - $1,000,000 - $1,000,000+ |
| District Context | Large urban/suburban district. 31,560 students across 38 schools district-wide. The engagement serves 24 elementary schools and 5 junior highs using i-Ready Classroom Mathematics (~1,054 teachers), plus instructional coaches and building/district leaders. 31,560 students across 38 schools district-wide. The engagement serves 23 elementary schools and 5 junior highs using i-Ready Classroom Mathematics (~1,054 teachers), plus instructional coaches and building/district leaders. Year 3 of K–8 i-Ready Classroom Mathematics implementation. Overall goal: deepen discourse-led instruction through the Try–Discuss–Connect framework — building student ownership, perseverance, and deeper mathematical understanding — and support leaders in reflecting on practice and monitoring implementation by focusing on targeted Effective Mathematics Teaching Practices (Facilitate Meaningful Discourse; Pose Purposeful Questions). |  |  |

Sample Scope and Sequence

| Timing (you may choose to use specific days/months or frequency) | Participants | Name of PL (either specific workshop title, coaching, etc) and format( Virtual, in-person, hybrid) | Description |
| --- | --- | --- | --- |
| Wed, July 22, 2026 (4 sessions: K–1, 2–3, 4–5, 5–8) | New math teachers; K–8 math teachers from each elementary school and junior high; instructional coaches and school leaders as able | Preparing to Teach i-Ready Classroom Mathematics with Integrating Digital Resources Facilitated PL Session – In-Person (+ self-led Online Educator Learning Course) | Teach Lesson 0 to establish a classroom where students make meaning of mathematics through purposeful conversation; use the Teacher’s Guide to plan and implement instruction; motivate and prepare students for the Diagnostic; and use digital components for instruction, practice, assessment, and differentiation. Follow-up Collaborative Learning Extension: Establishing Routines Using Lesson 0. |
| July 23 (Gr K–6) & July 24 (Gr 7–8), 2026 | K–8 math teachers from each elementary school and junior high teachers; instructional coaches; school leaders as able | Making Math Accessible through Purposeful Questioning (7–8) AND Leveraging Mathematical Representations to Support Student Learning (K–6) Facilitated PL Session – In-Person | 7–8: Describe questioning patterns that advance student thinking, align questions with the Try–Discuss–Connect framework, and respond strategically to sustain and deepen discourse. K–6: See and use the connections between mathematical representations to develop student understanding across multiple ideas over time. |
| Back to School — July 2026 (before the first Diagnostic) | New-to-district and new-to-i-Ready teachers | Administering the Diagnostic Online Educator Learning Course | Learn key steps before, during, and after the Diagnostic; understand how to prepare and motivate students to take the Diagnostic; and use data to track completion. Accessed in i-Ready Connect (~1.5 hours). |
| August 2026 (launch) | Single school site: up to 9 active teachers; school leaders/instructional leaders | Coaching by i-Ready — Instructional Coaching: Leader Pathway (Launch & Planning) In-Person | Launch the add-on instructional coaching package (Classroom Focus) for a single school site: 15 PL days across the year delivered as 3 coaching cycles and 3 learning walks, plus Teacher Learning Cohort sessions, to strengthen teacher practice and build leader capacity to support teaching and learning. |
| Throughout the 2026–27 school year | Teacher cohort (single school site) | Coaching by i-Ready — Teacher Learning Cohort Sessions In-Person | 9 cohort-based professional learning sessions that reinforce and extend the instructional coaching pathway across the year. |
| Sept 1, 2026 (AM/PM sessions) | K–8 math teachers from each elementary school and junior high including instructional coaches; school leaders as able | Developing Mathematical Thinkers through Instructional Routines with Personalized Instruction Orientation (New K–8 teachers) Facilitated PL Session – In-Person or Interactive Team Session (live online) (+ self-led Online Educator Learning Course) | Draw connections between the Try–Discuss–Connect routine and mathematical practices; use the routine to develop conceptual understanding through shared student thinking, productive struggle, and authentic discourse; and learn how i-Ready Personalized Instruction complements teacher-led instruction. |
| Sept 24, 2026 | Leaders from each elementary school and junior high; district leaders | Leading an i-Ready Classroom Mathematics Implementation III Facilitated PL Session | Analyze Diagnostic 1 data and understand the importance of monitoring i-Ready usage. |
| Sept–Oct 2026 | School leaders; instructional coaches | Coaching by i-Ready — Learning Walk 1 In-Person | First of three structured classroom learning walks to monitor the health of implementation and inform next steps for coaching. |
| October 2026 | Single school site: up to 9 active teachers; instructional leaders | Coaching by i-Ready — Instructional Coaching Cycle 1 In-Person | First of three coaching cycles: co-plan, co-facilitate, and co-reflect with teachers to strengthen instructional practice. |
| Nov–Dec 2026 | School leaders; instructional coaches | Coaching by i-Ready — Learning Walk 2 In-Person | Second structured classroom learning walk to monitor implementation and inform next steps for coaching. |
| December 2026 | Single school site: up to 9 active teachers; instructional leaders | Coaching by i-Ready — Instructional Coaching Cycle 2 In-Person | Second coaching cycle: co-plan, co-facilitate, and co-reflect with teachers to strengthen instructional practice. |
| Jan 11, 12, 19, 25, 26, 28, 2027 (1 day per site) | K–8 math teachers from each elementary school and junior high including instructional coaches; school leaders as able | Tailored Support Session (1 day per site) Facilitated PL Session – In-Person | Select from content such as: Connecting Mathematical Ideas Around Selected and Sequenced Strategies; Shift Student Actions through Intentional Planning; Rethinking Purposeful Planning; Interactive Video Study (Try–Discuss–Connect Framework). |
| Feb 18, 2027 | Leaders from each elementary school and junior high; district leaders | Leading an i-Ready Classroom Mathematics Implementation III Facilitated PL Session – In-Person | Reflect on current instructional practice and observations from the Leadership Look For Visits; analyze Diagnostic 2 data; discuss Typical and Stretch Growth; and understand the importance of monitoring i-Ready usage. |
| Feb–Mar 2027 | School leaders; instructional coaches | Coaching by i-Ready — Learning Walk 3 In-Person | Third structured classroom learning walk to monitor implementation and inform next steps for coaching. |
| March–April 2027 | Single school site: up to 9 active teachers; instructional leaders | Coaching by i-Ready — Instructional Coaching Cycle 3 In-Person | Third coaching cycle: co-plan, co-facilitate, and co-reflect with teachers to strengthen instructional practice. |

Includes any travel related expenses, etc.