Sample Scope and Sequence of Professional Learning Engagement

This overview represents the services for one client of the professional learning partner.

| Curriculum or Content Area | Benchmark Advance ELA Intervention (K-3) |  |  |
| --- | --- | --- | --- |
| Type of Professional Learning | Ongoing Implementation |  |  |
| Total Cost Range | - Less than $50,000 - $50,000 - $100,000 - $100,001 - $500,000 |  | - $500,001 - $1,000,000 - $1,000,000+ |
| District Context | Large urban district Goal: Support schools to shift to instructionally coherent literacy instruction. |  |  |

Sample Scope and Sequence

| Timing | Participants | Name of PL and format | Description |
| --- | --- | --- | --- |
| May-July | District leaders | Designing Instructionally Coherent Intervention Systems (In-Person) | Facilitate district academic and intervention leaders to design new intervention models, processes, and tools. |
| June | School Leadership Teams | Instructional Coherence 101 (In-Person) | Build investment & understanding in instructional coherence: what is it and why does it matter for kids? |
| September | School Leadership Teams | Coherent Intervention Model Launch (In-Person) | Roll out the new coherent intervention model, process and tools to school teams; support school teams to review diagnostic data, create instructionally coherent student groupings, and identify what to use from the Tier I material to address identified student needs. |
| October | School Teachers & Interventionists | Using Benchmark Advance Effectively During Intervention (In-Person) | Support interventionists to understand the design and intention of the Benchmark Advance intervention materials and how to most effectively use them to provide coherent student support. |
| Bi-weekly | School Leadership Teams | Ongoing Check-ins (Virtual) | Twice monthly check-ins to support school teams to identify and trouble shoot challenges. |

Includes any travel related expenses, etc.